Commercial Systems Roadmap – Software Selection

Project Customer:  Commercial Operations		Project Manager: Bret Blackford

Project Start Date: 01/21/2024			Requested Delivery Date: April 26, 2024

Budget Expectation: $4,000,000.00			Change #: CHG0034034

Project Priority: High					Project Class: Large

Project Risk: High					Project or AFE #: 24ARI013

Project Background:

Perficient was engaged to perform a review of the applications in the Commercial function. The outcome of this engagement was a roadmap of work to improve the Commercial systems landscape in alignment with business and IT strategy.

Perficient recommends that Arch Resources undertake an 18–24-month program to replace the ERP functionality of the RMS suite (RMS and associated macro-enabled spreadsheets, reporting, and analytics). Replacements should follow the current IT strategy for ERP, technology stack and future support via 3rd party vendor partners.

​

Determination of which applications will replace various components of the RMS suite remains a need at a detailed level. Perficient proposes a Software Selection Process, immediately followed by a Target Architecture Engagement to ensure that the right tools are selected based on business needs, and that the tools can be unified appropriately using standard integration and workflow automation tools. ​

Project Summary:

Perficient is being engaged to work with Arch in selection of commercial, off-the-shelf (COTS) software packages to support the implementation of the Commercial Applications roadmap.

Scope:

Using Perficient’s Envision Online platform selection tool, Perficient will validate existing and gather further Arch-specific requirements as needed. The team will also work with Arch personnel to identify and assess the ability of COTS packages to address and implement those requirements.

Goals:

Define

- Define capabilities by process from phase 1​

  - Mine-to-Port

  - Customer Relationship Management (CRM)

  - Opportunity to Cash

  - Inventory Management

  - Contract Management

  - Accounts Payable

- Review capabilities with Arch Process Owners​

- Translate capabilities to Use Cases​

- Communicate Use Cases to software vendors

Demonstrations

- Identify software vendors as potential fit​

- Review use cases with vendors​

- Schedule demonstrations​

- Score vendors based on ability to execute use cases

Software Selection

- Select best fit package(s)​

- Assist Arch and Procurement resources to obtain from the COTS providers their implementation timelines and estimates, and ongoing licensing cost estimates for the selected COTS packages.​

- Finalize commercial systems selection

|  | Phase 1 Software Selection | Phase 2 Technical Architecture |
| --- | --- | --- |
| Duration | Fourteen (14) weeks | Seven (7) weeks |
| Start Date: | January 29, 2024 | April 8, 2024 |
| End Date: | May 3, 2024 | May 24, 2024 |

Attachments - Additional Key Documents

| # | Description | File(s) |
| --- | --- | --- |
| 0 | TEAMs/SharePoint location of documents obtained during the 2023 investigation phase | SharePoint directory |
| 1 | Early architecture considerations from Lily Chen and Paul Demzik - 11.10.2022 Commercial Systems Modernization 2 |  |
| 2 | 2020 IT Strategic Review and Roadmap - presentation (SharePoint here) |  |
| 3 | 2020 Strategic IT Assessment and Roadmap - report (SharePoint here) |  |
| 4 | 2023 Arch Commercial Systems Assessment and 3-Year Roadmap (SharePoint here) |  |
| 5 | 2023 Commercial Systems Review and Roadmap (SharePoint here) (mtg. recording here) |  |
| 6 | AFE 24ARI013 3rd party costs; $3,115,000.00. Arch Internal Costs; $ 885,000.00. Total AFE; $4,000,000.00. |  |
| 7 | Draft Project Charter |  |
| 8a | Kickoff Meeting – Feb. 1, 2024 | Link here |
| 8b | Key Stakeholders – (SharePoint link) |  |
| 8c | Project Plan – Feb. 5, 2024 (SharePoint link .xlsx, .pdf) | Perficient Smartsheet link |
| 9 | Feb. 8, 2024 email to Paul Demzik with preliminary Deal Making/ Entry Process flow and requirements |  |
| 10 | Weekly Project Status Reports | SharePoint link here |
| 11 | Initial scheduled meetings - 02/06 - Bret and Tony Oster meet with Paul Demzik to review Project Plan - 02/12 - Perficient team meet with Kent Smith (1-hour) - 02/14 - Perficient team meet with Kent/Barb/Lily (2-hours) - 02/15 - Perficient team meet with Kent/Barb/Lily (2-hours) | SharePoint link to sessions info here |
| 12 | Various Session Recordings – requirements gathering and vendor demos | SharePoint link to sessions info here |
| 13 | The following COTS vendors were selected as potential solutions: - iON (QMastor & Aspect) - Pulse Mining Systems | SharePoint link to vendor demos here |
| 13a | Pulse demos - April 10 - April 30 |  |
|  | iON demos (Qmastor & Aspect) - April 1 - April 29 - May 30 - June 3 |  |
| 14 | iON next steps meeting – June 4, 2024 - Implementation Assessment |  |
| 15 | Boomi selected for integrations |  |
| 16 | June 4, 2024 email summarization on iON path forward |  |
| 17 | Discussion with Accounting on Capitalization vs Expense |  |
| 18 | Technical Architecture phase - expected to start June 17 |  |
| 19 | June 14, 2024 project update |  |
| 20 | June 24, 2024 Perficient Final Deliverables Report – summary and Vendor Recommendation |  |
| 21 | Perficient’s Technical Architecture (TA) timeline - Phase 2 - SoW |  |
| 22 | June 26, 2024 Technical Architecture (TA) kickoff |  |
| 23 | iON Aspect and Qmastor Implementation Analysis - 1st draft June 27, 2024 |  |
| 24 | iON implementation Analysis (IA) Service Order Form (SOF) - 1st draft June 28, 2024 |  |
| 25 | iON Coal Logistics and Order Management: iON Executive Summary - 1st draft June 27, 2024 |  |
| 26 | Perficient identifies risk to Technical Architecture (TA) phase - XFA/Excalibur architecture and ITGCs |  |
| 27 | July 23 meeting with Perficient and John Ziegler to discuss project risk identified with XFA/Excalibur |  |
| 28 | July 29 email notifying Matt Giljum and Paul Demzik of Implementation Analysis on-site schedule |  |